ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Center for development of the Third North East planning region

## Country background

Republic of North Macedonia in its area and population is one of the smallest states in Europe. Its area stretches 25 713 km ². There are about 1.8 million inhabitants. Although it is a relatively small country, it is characterized by the presence of numerous tourist values. In this area, notably is the presence of natural and anthropogenic attractive values. North Macedonia, landlocked country of the south-central Balkans. It is bordered to the north by Kosovo and Serbia, to the east by Bulgaria, to the south by Greece, and to the west by Albania. The capital is Skopje. Along with the rest of the Balkan Peninsula, Macedonia underwent an impressive economic transformation after 1945 in this case within the framework provided by Yugoslavia’s system of “socialist self-management.” Even so, Macedonia remained the poorest of the Yugoslav republics and was included throughout the communist period in the list of regions that merited economic aid from wealthier parts of the federation. While this status undoubtedly brought much investment, several projects were placed without adequate attention to the supply of materials or access to markets. A prime example was the choice of Skopje as the site for a steel industry. Although socialized production dominated industrial and commercial life after the communists’ rise to power in 1945, the private sector remained important in agriculture, craft production, and retail trade. About 70 percent of agricultural land was held privately, accounting for some 50 percent of output. However, privately owned enterprises were typically traditionalist in structure and outlook, and, even after the liberalization of the communist system in 1991, they were unable to develop a dynamic economic role. The location of the republic along the Morava-Vardar route from Belgrade, Serbia, to Thessaloniki, Greece, has endowed it with reasonably modern road and rail links on a northwest-southeast axis. North Macedonia’s historic rail link with Greece passes through Bitola. The development of tourism in the Mavrovo - Ohrid area ensured new road building in the west. Airports at Skopje and Ohrid serve international destinations.

## Current situation in the sector

Tourism in North Macedonia is a large factor of the nation's economy. Macedonian tourism in the past ten years has been on the rise and has seen an increase of about 140%. It promoted the country as an interesting tourist destination in the Balkans and aroused interest for guests from several countries of the world to visit it. The potentials that it possessed as well as its tourist-geographical position represent a basic assumption in the determination of the state to put the tourism industry in priority activities. Tourism development should be aimed at improving not only the economy but also towards tourism and the economy as a whole. Balanced development, underdeveloped spatial entities, vitalization and promotion of attractive values, protection and improvement of the environment in areas of national interest, establishing a cultural attitude towards nature, natural and cultural heritage, raising the educational level of visitors and health-recreational benefits are well-known tourist functions. Diversity in Macedonia is the main word to qualify its tangible and intangible heritage. The major stake of tourism development in Macedonia is now to find the appropriate sustainable marketing offers and enhancement tools to reveal them as key tourist resources. Macedonia first determines itself by the variety and number of cultural heritage sites, directly inserted in its rural, mountain and urban landscapes. The Northeast Region is one of the eight statistical regions of Macedonia. It is located in the north-eastern part of the country and is bordered by the Skopje Region and the Eastern Region. The region has many tourist attractions and cultural landmarks that attract a large number of visitors. The most important are the locations of Kuklica, Kokino, Cocev Kamen and the monastery St. Joakim Osogovski. This region is characterized by protected natural areas and ecological corridors of the national ecological network for connecting protected areas and environmentally important areas. As representative areas are defined several sites such as Kumanovo Kozjak, which is proposed for a Nature Park despite the rocky sections important for nesting several species of birds of prey, the area is the ultimate northern range of the spread of some Mediterranean species. In the remnants of oak and beech forests on the northern slopes, other significant bird species are also found. Tourist trends in the Northeast region have undergone relatively great changes in recent years. The needs of the tourists who visit the region are specific and segmented, and according to them, the tourist offer was adjusted. Increasing attention is paid to the creation of development plans, programmes and strategies in those destinations.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

Fostering the integrated and inclusive social, economic and environmental local development, culture, natural heritage, sustainable tourism and security, in areas other than urban areas.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

Increasing of the competitiveness of the tourism through Introduction of digital tourism products, promotional marketing, all-season planning and up-scaling of specific knowledge of tourism professional

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

# Lot 1:     Organized training, developed integrated joint tourist offers, organized workshop, developed analyze and formulated tourism infrastructure strategy

# Lot 2:      Organized tourist promotional tour, design and implemented promotional marketing

# Lot 3:      Developed digital tourist products and produced tourism documentary movie/video

- Lot 4:     Formulated Communication plan and 300 Promo sets of materials, leaflets, banners, project web page and facebook.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Good cooperation between all parties involved in the contract completion.

There is interest among target groups to participate in the Living Lab

## Risks

No significant risks have been identified for the completion of the contract

# SCOPE OF THE WORK

## General

### Description of the assignment

The Consultant should provide expertise in the area of the:

- For LOT 1 - Organization of capacity building, organization of project events and/or development of studies in area of sustainable tourism, infrastructure and/or other relevant areas

- For LOT 2 – Marketing, development of campaign, tourism and marketing consultancy, organization of tours and promotional events and/or other relevant areas

- For LOT 3 – Development of digital products, mapping, development of scenario and shooting of videos or movies and/or other relevant areas

- For LOT 4 -   Design and printing of promo materials, visibility and/or other relevant areas

for successful implementation of project. The assignment of the present contract is to provide consultancy support through knowledge and expertise in the providing relevant services.

### Geographical area to be covered

North East planning region and CB region of North Macedonia and Bulgaria

### Target groups

Local and regional public authorities, interested groups including NGO’s, tourist services providers and tourists.

## Specific work

4.2.1 LOT 1 Consultancy

4.2.1.1 Organization of training

The consultant should organize training (2 days) with subject “Hospitality and Guest Experience- Concept of Customer Experience in Tourism”. Training should be organized in Kriva Palanka or Kumanovo for 20 participants (10 from Bulgaria and 10 from N. Macedonia). The Consultant should provide trainer with relevant background and experience and moderator for holding the training. Also the consultant should provide adequate hall in Kumanovo or Kriva Palanka to hold the training with the capacity of 20 participants, then should provide accommodation ( Half pension) for 20 participants in double rooms, lunch for 20 persons with a choice of one of three courses, dessert and salad, and includes one non-alcoholic drink per participant for each of the two days of the training, two coffee breaks for each day of the training, including coffee, tea or juice for each participant, as well as drinking water ( 2 x 0,5l per day and participant) in front of each participant during the training. The Consultant should develop a curriculum for the training. Trainer and moderator should prepare the needed trainings materials for the proper organization of the training, to hold the training and to prepare report. Trainings should be conducted through participatory methods, facilitation and introduction of creativity techniques. Mix of interactive and frontal activities across the day of the trainings with a core part for both the interactive and frontal session should be implemented. Possible techniques that should be used are, as it follows: interactive exercises, video materials, bottom-up methodological presentation of Case Studies from worldwide, questions and answers as well as relevant power point presentations. Method of Knowledge Café should be used to Encourage Each Person’s Contribution and to provide interaction and the exchange of ideas among participants.

For the exact date of holding of training the respective Consultant will be informed at least 30 days before the planned date of holding of training.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. ).

4.2.1.2 Organization of the work shop

In the frame of the process of development of Tourism infrastructure strategy, the consultant should organize one workshop, two days long in Kriva Palanka or Kumanovo. On workshop 20 represents (by 10 of Bulgaria and North Macedonia) of tourism sector SMEs will participate. The Consultant should provide trainer with relevant background and experience and moderator for holding the workshop. Also the consultant should provide adequate hall in Kumanovo or Kriva Palanka to hold the training with the capacity of 20 participants, then should provide accommodation ( Half pension) for 20 participants in double rooms, lunch for 20 persons with a choice of one of three courses, dessert and salad, and includes one non-alcoholic drink per participant for each of the two days of the training, two coffee breaks for each day of the training, including coffee, tea or juice for each participant, as well as drinking water ( 2 x 0,5l per day and participant) in front of each participant during the training. The Consultant should develop a curriculum for the workshop. Trainer should prepare the needed trainings materials for the proper organization of the workshop, to hold the workshop and to prepare report.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.1.3 Formulation of the tourism infrastructure strategy

In the frame of this activity, Consultant should formulate tourism infrastructure strategy for North East region of North Macedonia and area of Hisarlak (Kuystendil) and St. Ana in Nevestino in the Republic of Bulgaria. Within this strategy, an analysis for the North East region of North Macedonia and area of Hisarlak and St. Ana in Nevestino should be done of the existing tourist infrastructure with the exception of the transport infrastructure (roads, railways, airports) and transport. The analysis should be done from the aspect of quality and quantity of this type of infrastructure, as well as from the aspect of enabling inclusive tourism, that is, the accessibility of the tourist infrastructure for people with special needs. Also, Strategy should identify opportunities across the whole area to protect and enhance tourism infrastructure. Tourism infrastructure strategy has three aims:

- to set out what actions and interventions are needed to improve the accessibility of the existing tourist infrastructure and enable the development of inclusive tourism

- to identify the tourist infrastructure needed to create conditions for the development of tourism

- to carry out an assessment of the necessary financial resources and to identify possible sources of financing

Taking into consideration that the municipality of Kriva Palanka and the whole North East region have a relatively small accommodation capacity, within the framework of the strategy, the possibility of developing a system of 'home stays', which enable visitors to stay with local people, should be analyzed.

Process of development of strategy should include:

- Analysis of the existing tourism infrastructure in the North East Planning region

- Identification of demand drivers and supporting visitor infrastructure.

- Definition of tourism infrastructure challenges

- Addressing tourism infrastructure priorities

- Development/Design of tourism infrastructure strategy

As a part of the strategy development process – one workshop will be organized in Kumanovo ( 20 participants) – activity 4.2.1.2 Organization of the work shop

With support of the engaged expert from Bulgaria (PP5)  a common strategy for tourism infrastructure should be formulated.

At least two relevant experts should be proposed by the consultant in submitted offer.

4.2.1.4 Development of integrated joint tourist offers

Activity focuses on developing joint and internationally competitive tourism offers in cultural and adventure tourism niches and their global promotion (WP4), thus contributing to the promotional of the region as a desirable tourism destination

Under the responsibility of Contracting Authority, sustainable new integrated competitive regional tourism products should be developed by the Consultant. As a part of this activity developed tourist offer should be tested and implemented in order to develop the potential of cross-border tourism by increasing the economic benefits of the sustainable use of its resources.

Within the activity, the existing separate tourist offers for the municipality of Kriva Palanka, the North-Eastern planning region, the municipalities of Kustendil and Nevestino should be analyzed and at least two most viable regional tourism routes and offers should be created. Through up-scaling of the existing separate offers, several joint integrated tourists offer should be created by the consultant.

Offers should be created for all seasons and should contain different experiences/activities depending on the selected type of tourism. On the end of the activity, an all-season, integrated tourism offer which will feature three individual tourist products valorising the unique potential for culture, adventure and bike tourism in the municipalities involved in the project should be created. The offer should be developed together with the local community and local tourism service providers.

The new tourism products should be pilot tested during implementation of project and will be promoted and advertised in the frame of the activities from LOT 2.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.1.5  Analyze of the potential tourism market segments

In order to effectively promote the products which will be created in LOT 3, detailed analysis of the tourist market should be made in order to identify the market segment in tourism to whom promotional marketing will be directed. Through this analysis, the profile of potential tourists who would be interested for created tourist offers and products should be created. In this way, the profile of the customers to whom the promotional marketing would be directed will be identified.

Adventure products like adventure parks which will be constructed in Kalin Kamen and Kustendil would target adventure seekers and the promotional marketing should be focus on these potential customers, for example, while less adventurous visitors might prefer other thematic tourist offers  where they could enjoy a quieter vacation in a safe context near a cultural heritage or in the nature.

The analysis should be carried out by the consultant (tourism experts). The analysis should begin with the collection of existing data related to tourism in the CB region, specifically for the North-East planning region in North Macedonia and the municipalities of Nevestino and Kustendil in Bulgaria. Following the analysis of the available data, segmentation of tourist market should be done on the base of the four fundamental criteria for segmentation: geographic, demographic, psychographic and behavioural.

At the end of this activity, we should get a clear picture of the potential market segments to which the promotional marketing will have to be directed.

4.2.2 LOT 2 - Marketing

4.2.2.1 Promotional marketing of created tourist offers

The Consultant should design and implement marketing activities (campaign) with the aim promotion of the developed offers and other tourist products. Within the activity, the social media marketing (SMM) tools and targeted advertising should be used to present developed offers and tourist products  in front of possible audience on social networks, such as Facebook. Campaign should be implemented within two months through Facebook and it is expected that the promotional advertisement to reach between 84,000 and 216,000 people, who have shown interest in traveling and the algorithm considers them to be frequent travellers. In the countries (Poland, Germany, Turkey, Holland, etc.) from which, according to statistical data, the largest number of tourists come in both countries, it is expected that the promotional advertisement would reach some between 228,000 and 426,000 people. Within LOT 3, it is planned to record a short video (short version of the documentary movie) of the advertised place showing the best sides and have contact numbers of accommodation facilities so that it can be scheduled immediately, which will increase the overall "awareness" of the place and the number of reservations will increase. Link from the video, should be on the Facebook ad

The consultant should Design and develop Facebook ad with relevant links to the developed tourist offers, created digital tourism product and location of the adventure parks and cultural heritage sites in the Municipalities partners in the project. The ad should be design respecting all requirement of the EU visibility guidance. The campaign should be implemented in 3 Balkan and 5 EU countries

Also, following sub-activities should be implemented in order to increase the popularity of the created tourist offers:

- email newsletter should be used in promotional marketing campaign to provide wider audience with important updates, offerings, and news that’s relevant to developed tourism infrastructure and tourist products

- Placing online banners on certain websites, where potential clients will be able to created tourist products and offers. On the base of the conducted analyse in activity 4.1 list of desired web sites where online banners will be advertised should be prepared. Websites where banners should be advertised will be the types of sites of target audience visit.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

      - Organization of tourist offers promotional tour

Within this activity, a tourist tour for representatives of the tourist agencies and tour operators should be organized by the Consultant. This tour should last 3 days and 10 representatives of tourist agencies and tour operators who work at the national and international level on both sides of the border will be invited to it, with the aim of promoting all project tourist infrastructural interventions and created digital tourism products within the project.

As part of the tour, the invited representatives of tour operators and travel agencies should visit the two created parks in Kriva Palanka and Kustendil, where they will have the opportunity to experience an adventurous experience, then they will be presented with all the developed digital products (in Kokino) and the created tourist themed offers. The overall offer from the tourist aspect of the municipalities that are part of the project should be presented to the participants of this promotional tourist tour, as well as the traditional food and drinks and other traditional tourist products like souvenirs. Created promotional materials should be distributed among the tour participants. The tour should end with the presentation of the promotional documentary movie, separate videos and short video (LOT 3). Two professional tourist guiders should be engaged to lead the tour. Also, the consultant should provide adequate accommodation for 10 participants for two nights in single room on the base of Bed and Breakfast ( BB), Food and beverages ( lunch and dinner), transport and all other needs for organization of promotional tour.

- The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

- 4.2.3 LOT 3 - Development of digital products

- 4.2.3.1 Development of digital tourist products

The implementation of new technologies is closely related with the support of innovations in tourism services. In order to acquaint tourists with the possibilities offered by the localities covered by the project idea, the following digital products should be created within the framework of this activity:

- Virtual tour for the four improved tourist infrastructures - Adventure Park, Hisarlka area, Adventure Park in Kalin kamen area, site in Sveta Ana area, Smolichano village, Nevestino Municipality, Kokino area.

- In combination with these virtual tours, two joint virtual tours will be prepared that correspond to the created tourist offers from LOT 2 tourism routes and multi days offers (culture and adventure/mountain), i.e. a virtual tour on the topic of culture and a virtual tour on adventure/mountain theme.

- Virtual reality with VR glasses for the four improved tourist infrastructures - Adventure Park, Hisarlka area, Adventure Park in Kalin kamen area, Kokino area. The VR application will be placed in the museum in Kumanovo and in other places /Kyustendil, Nevestino, Kriva Palanka/, multiplying what has been achieved within the framework of the project "Light from the past", financed by the CBC program, and tourists will be able to visit through "virtual reality" different places through an interactive 3-5 minute VR experience.

- Augment reality for Kokino - Software for Augmented Reality application with which it will be possible to see the setting of the sun in the markets of the rock, which only happens on certain days of the year (summer long diary 21.6 and ritual marker 31.7) and at a specific time. That's how they measured time, and through this application visitors will be able to experience those moments outside of the precisely defined time frames. By scanning a code and activating in certain markers they will see how the sun coincides with the rocks on only two days of the year

- Digital bike map

- The aim of the sub-activity is to map the potential of the hiking/biking trails and put them into operation as a networked system for mountain recreational tourism in the Mountains in the cross-border region. This activity should be focus on mapping of bike lanes in the cross-border region of Kriva Palanka and Kumanovo and creation of an integral digital bike map. Process of mapping should start with collection of existing data about existing bike paths and interviews with the represents of local and regional bike associations. After collection and analyze of existing data, process of mapping of bike trails should start on the ground with marking of bike trails. Within the scope of the activity, it is planned to map a network of cycling and other types of tourist trails, with a total length of at least 30 kilometres. After the trail mapping is completed, a digital bike trail map should be created. Created maps should be presented on the QR codes. Beside the digital map, the QR code should contain all developed digital products and tourist info  for municipalities including in the project, including and developed tourist routes. The codes should be placed on over 50 places.

Following digital product should be delivered:

- Four separate virtual tour for Kokino, Hisarlak, Kalin Kamen and St.Ana – each virtual tour will lasts at least 2 minutes and experience of visiting the attractions of the region will be shown. The virtual tours will be shown in the form of walking or visiting the locations covered by the project.

- two joint thematic virtual tours. In combination with separate virtual tours, two joint virtual tours will be prepared that correspond to the created tourist offers from activity 3.1 - virtual tour on the topic of culture and a virtual tour on adventure/mountain theme. Each virtual tour will last at least 2 minutes.

- Three virtual reality. Virtual reality with VR glasses for the improved tourist infrastructures - Adventure Park, Hisarlka area, Adventure Park in Kalin kamen area, Kokino area will be created.

- Augment reality for Kokino. Software for Augmented Reality application with which it will be possible to experience the fall of the sun in the markets of the rock which only happens on certain days of the year

- Digital bike map. On the base of the Mapping of bike lanes in the cross-border region Kyustendil – Kriva Palanka – Nevestino – Kumanovo  one joint integral digital map will be created. Created map will be uploaded on the several specialized biking web platforms and on the google map platform.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

- 4.2.3.2 Production of tourism documentary movie/video

In the frame of this activity documentary movie should be created. The movie should be 6 to 8 minutes long, following the example of travel documentaries movies broadcast on the History I Nacional Geographic channels. It should be a documentary-play approach with the participation of a narrator and historians (documentary approach) and a team of professional actors (play approach).

Process of producing of documentary movie should start with developing scenarios and recording the locations with a camera and drone and taking photos. From these recordings, 4 promotional videos (1.5 to 2 minutes), by one for each locality covered with the project should be developed. On the base of these developed videos, one joint promotional travel documentary movie/video should be developed.  In this movie all localities should be presented as one joint tourist destination and two developed tourist packages should be presented as a tourist's journey through created routes, visiting all cultural sites and doing all adventure activities. Also, short video long one minute should be created. This short video will be used for promotion of the created project results, through implementation of the activity for promotional tourism marketing. Created promotional travel documentary movie should be attached on few specialized travels on-line platform, including you tube.

The overall service requirements:

-	Develop overall video concept -Design and develop the story of the TV clip in coordination with the project partners. The concept must be pre-approved by the Contracting Authority;

-	Shoot video materials- Preparation of video materials for production and post-production;

-	Review the video materials and make a selection of the best shots to be used for the TV clip;

-	Provide all the necessary documentation in case of shooting in situation where permission is required;

-	Provide all post-production support (editing, mixing, transitions, titles, credits and effects);

-	Cut-editing and submission of the first – long version of the TV clip and the short video clip;

-	Subtitling –inserting translation of audio recorded materials on language requested by the Contracting Authority (Bulgarian, Macedonian or English);

- -	Production of the final version of both TV clip (indicative title) - short and full version of the TV clip

- 4.2.4 LOT 4 Visibility:

- 4.2.4.1 Development of the communication plan

Consultant should develop communication plan that will define the communication strategy of the project and will be used as a guide by the project partners to maximise its dissemination impact. The project communication plan should define the dissemination objectives of the project, describe the target groups of communication and dissemination activities and indicate the proper means, communication channels and materials required to reach target groups and achieve objectives. The communication strategy should include definition of aims and objectives, the identification of target groups and the overall decision about the most appropriate means, channels and resources to be deployed within a specified time-horizon. Implementation includes the planning and outlines for the communication infrastructure, activities, organization of events and activities, monitoring and assessment of impact. Definitions of concepts and justification will be outlined for each dissemination activity.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.4.2 Creation of website and facebook page

Activity includes the design and putting in operation a web-site and facebook page.

Consultant should develop website which will serve as a platform for exchanging information, ideas and good practices in the area of the green infrastructure, building contacts among main key actors and networking. Also, on the created web platform all promotional and communication materials should be presented. Project web portal should be designed, developed and implemented in 3 languages: Bulgarian, Macedonian and English. The web site should be dynamic and should have capabilities for supporting the whole range of information related with the green infrastructure.

Consultant should present the graphic design of the website to the all Partners, who have to approve it before the development and implementation phases are undertaken. The inputs in the Facebook profile should be blog-like in nature.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.4.3 Visibility materials

The Consultant should support the Centre for Development of the Third North East Planning Region in overall process of implementation of the project trough design, printing and delivery of consumables for training and project promotional materials. Following materials and consumables should be designed, printed and delivered:

| Visibility and promotional materials | Quantity |
| --- | --- |
| banners, colour printed | 3 |
| Folders A4 colour printed | 300 |
| USB printed | 120 |
| pens | 300 |
| Notepad A5 colour printed | 300 |
| Promotional brochures (500) 12 pages A4 | 300 |
| leaflets (500), A5 | 300 |

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

## Project management

### Responsible body

The Contracting Authority is Centre for Development of the Third North East Planning Region, Republic of North Macedonia and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by Centre for Development of the Third North East Planning Region, Project office – which is responsible for implementation of project.

### Management structure

The project “Cross-border attractiveness - smart tourism in region Kyustendil - Kriva palanka - Nevestino” is implemented by Municipality of Kuystendil from Bulgaria in partnership with Municipality of Kumanovo and Centre for Development of the Third North East Planning Region. Centre for Development of the Third North East Planning Region will be the Contracting Authority responsible for regular coordination as well as coordination with the other partners and will have the overall responsibility of implementation of the project activities in Republic of North Macedonia.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

North East Planning Region

## Start date & period of implementation of tasks

The intended start date is 10.07.2025 and the period of implementation of the contract will be 20 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Minimum requirements for experts are not defined

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contracting authority.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

- Interim report of maximum 3 pages (main text, excluding annexes). This report shall be submitted no later than ten month after the beginning of the period of implementation of tasks.

Final report of maximum 3 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

## Submission and approval of reports

The report referred to above must be submitted to the project coordinator. The project coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

LOT 1

- Organized training,

- Organized workshop,

- Developed two most viable thematic regional tourism routes/offers,

- Developed analyze and

- Formulated tourism infrastructure strategy

LOT 2

- Implemented promotional marketing of created tourist offers

- Organized tourist tour for representatives of the tourist agencies and tour operators

LOT 3

- Four separate virtual tour for Kokino, Hisarlak, Kalin Kamen and St.Ana

- two joint thematic virtual tours.

- Three virtual realities.

- Augment reality for Kokino

- Digital bike map.

LOT 4

- Developed communication plan

- Developed web page and facebook page

- Designed and printed promo materials:

- Banner (3)– roll up banner, printed in colour

- Folder (300)– hard cover with printed front in colour

- Pen (300)– printed

- notepad (300)– 50 A5 pages, hard cover printed in colour

- Usb (120)– at least 32 GB capacity, printed

- Promotional brochures (300)– 12 A4 pages, printed in colour

- Leaflets (300)– 2 A5 pages printed in colour

## Special requirements

N.A.

* * *